## ML Engineer A - PMR-DB
Week | Task Description | Input Required | Output Delivered | Synthetic Data Strategy | Pass/Fail Criteria | Est. Hours | Dependencies
1 | Study Bayesian inference fundamentals and probabilistic graphical models. Read Matrix22 docs (PMR-DB section, Evidence Graph). Learn probability theory, conditional probability, and Bayesian networks. | Matrix22 documentation PDFs (PMR-DB section, Evidence Graph construction) | Personal notes summarizing: (1) Bayesian inference concepts, (2) PMR-DB role in Matrix22, (3) Evidence graph structure | N/A - Learning phase | PASS: Can explain Bayesian inference, describe PMR-DB purpose, and sketch evidence graph structure. FAIL: Cannot articulate probabilistic reasoning flow. | 40 | None - independent learning
1 | Set up Python environment with PyTorch, SciPy, NetworkX. Complete PyTorch probability distributions tutorial. Implement simple Bayesian network for coin flips. | Python 3.11+, GPU access (AWS g4dn.xlarge) | Working Python environment, simple Bayesian network code example | N/A | PASS: Environment runs PyTorch probability code successfully. Simple Bayesian network produces correct posterior. FAIL: Import errors or incorrect probability calculations. | 40 | Backend Engineer: GPU instance provisioning
2 | Study calibration techniques: isotonic regression, Platt scaling, reliability diagrams. Implement calibration metrics (ECE, MCE, Brier score). Read papers on probability calibration. | Academic papers on calibration, scikit-learn documentation | Calibration module (calib.py) with isotonic regression and Platt scaling implementations. Documentation on when to use each method. | Use synthetic classification data with known miscalibration | PASS: Calibration module reduces ECE on test data. Reliability diagram shows improvement. FAIL: Calibration makes predictions worse or increases ECE. | 40 | None
2 | Design PMR-DB module architecture. Define interfaces for analog family input, world state constraints, and probability output. Write API specifications. | Matrix22 architecture docs, analog family data format (from ML Engineer B spec) | PMR-DB architecture document (pmr_db_architecture.md) with class diagrams, data flow, and API specs | N/A | PASS: Architecture clearly defines inputs/outputs, separates concerns, and supports world state constraints. FAIL: Unclear interfaces or missing world state handling. | 40 | ML Engineer B: Analog family data format specification
3 | Implement probabilistic aggregation over analog families. Build weighted averaging with confidence scores. Support heterogeneous analog sets. | Synthetic analog families (JSON format with confidence scores) | Aggregation module (aggregation.py) that combines analogs into probability distributions | Generate synthetic analog families: 50 historical scenarios with outcome distributions, varying confidence (0.5-0.95) | PASS: Higher-confidence analogs weighted more heavily. Output is valid probability distribution (sums to 1). FAIL: Uniform weighting ignoring confidence. | 40 | None - uses synthetic data
3 | Implement world state constraint enforcement (GREEN/YELLOW/RED). Build logic to suppress/constrain reasoning based on world state. | World state enum (GREEN/YELLOW/RED), threshold policies document | Constraint module (constraints.py) that gates reasoning based on world state | Mock world state generator with random GREEN/YELLOW/RED states | PASS: In RED, reasoning is blocked. In YELLOW, uncertainty intervals widened. In GREEN, full reasoning. FAIL: World state ignored. | 40 | Manager: World state threshold policy document
4 | Build uncertainty quantification module. Implement prediction intervals using analog outcome variance. Add epistemic vs aleatoric uncertainty decomposition. | Aggregated analogs with outcome distributions | Uncertainty module (uncertainty.py) computing confidence intervals and uncertainty decomposition | Synthetic analogs with varying outcome dispersion | PASS: Wide analog outcome variance → wide intervals. Narrow variance → tight intervals. Uncertainty increases when analog count is low. FAIL: Fixed intervals regardless of evidence. | 40 | None - uses synthetic data
4 | Implement calibration correction on final probabilities. Apply isotonic regression to ensure calibrated outputs. | Uncalibrated probability outputs from aggregation | Calibrated probability outputs, calibration validation report | Historical analog data with known outcomes for calibration fitting | PASS: Calibration curve approaches diagonal. ECE < 0.05. Brier score improves post-calibration. FAIL: Calibration worsens reliability. | 40 | None - uses historical synthetic data
5 | Build evidence graph construction algorithm using NetworkX. Link analogs → trajectories → outcomes. Implement temporal causality constraints. | Analog families with trajectory IDs and outcome data | Evidence graph module (evidence_graph.py) creating directed acyclic graph of reasoning | Synthetic analog families with fake trajectory IDs and timestamps | PASS: Graph is DAG (no cycles). Edges respect temporal ordering. All analogs linked to trajectories. FAIL: Cycles present or temporal violations. | 40 | None - uses synthetic data
5 | Implement evidence graph traceability: given a probability output, reconstruct the full reasoning path. | Probability output ID, evidence graph database | Traceability function returning all analogs and trajectories used in reasoning | Mock evidence graph with 100 nodes | PASS: Function correctly identifies all nodes in reasoning path. Traversal time < 1 second for 100-node graph. FAIL: Missing nodes or incorrect path. | 40 | None
6 | Integrate PMR-DB with HPVD module. Test with synthetic analog families from ML Engineer B. | ML Engineer B: Synthetic analog families output from HPVD | Integration test suite showing PMR-DB correctly consumes HPVD output | ML Engineer B provides 20 synthetic analog families | PASS: PMR-DB processes all analog families without errors. Probability distributions validated. FAIL: Import errors or format mismatches. | 40 | ML Engineer B: HPVD analog family output format
6 | Implement deterministic replay for PMR-DB. Ensure identical inputs produce identical outputs (random seed control). | Test analog families, fixed random seed | Replay validation report showing identical outputs across 10 runs | N/A - uses existing synthetic data | PASS: Hash of output identical across all runs. FAIL: Any variation in outputs. | 40 | None
7 | Build PMR-DB performance optimization. Profile code, optimize bottlenecks. Implement batch processing for multiple queries. | Profiling results, batch of 100 queries | Optimized PMR-DB with 2x speed improvement, batch processing support | Generate 100 random queries | PASS: Latency reduced by ≥50%. Batch mode 5x faster than sequential. FAIL: No performance improvement. | 40 | None
7 | Write comprehensive PMR-DB documentation including API reference, calibration methodology, and usage examples. | Existing code and architecture docs | PMR_DB_Documentation.md with API reference, examples, and calibration explainer | N/A | PASS: Documentation covers all public functions, includes 5+ code examples. FAIL: Missing key functions or no examples. | 40 | None
8 | Transition from synthetic to real analog families. Work with ML Engineer B to integrate real HPVD output. | ML Engineer B: Real analog families from historical market data | PMR-DB running on real data, validation report comparing synthetic vs real results | N/A - using real data | PASS: PMR-DB processes real analogs correctly. Calibration curves look reasonable. FAIL: Errors on real data or degenerate outputs. | 40 | ML Engineer B: Real HPVD analog families, Backend: Historical data access
8 | Implement reason code generation for probability outputs. Explain which analogs contributed most to final distribution. | Probability output, evidence graph | Reason code generator producing human-readable explanations | N/A | PASS: Reason codes identify top 5 contributing analogs with weights. Explanations are grammatically correct. FAIL: Unclear or incorrect attributions. | 40 | None
9 | Full integration testing with Manager authorization module. Test world state constraint enforcement end-to-end. | Manager: Authorization module with live world state classification | Integration test suite covering all world state scenarios (GREEN/YELLOW/RED) | N/A | PASS: All test cases pass. RED blocks reasoning. YELLOW constraints apply. GREEN allows full operation. FAIL: Any test failure. | 40 | Manager: Authorization module deployed
9 | Backend API integration. Expose PMR-DB functionality via REST endpoints. Test with Postman/curl. | Backend Engineer: FastAPI endpoints defined | PMR-DB functions callable via API, integration test passing | N/A | PASS: API returns valid JSON responses. Latency < 500ms per query. FAIL: API errors or timeouts. | 40 | Backend Engineer: FastAPI infrastructure
10 | Load testing and stress testing. Test PMR-DB with 1000 concurrent queries. Identify and fix bottlenecks. | 1000 concurrent test queries | Load test report, performance tuning document | Generate realistic query patterns | PASS: System handles 1000 queries without crashes. P95 latency < 1 second. FAIL: Crashes or memory errors. | 40 | Backend Engineer: Load testing infrastructure
10 | Fix bugs discovered during integration and load testing. Address edge cases. | Bug reports from integration testing | Bug fixes, regression test suite | N/A | PASS: All critical bugs fixed. Regression tests pass. FAIL: Critical bugs remain. | 40 | None
11 | Evidence graph database optimization. Implement graph indexing for fast retrieval. Add graph pruning for old data. | Production evidence graph database | Optimized graph storage with indexing, pruning policy | N/A | PASS: Retrieval time reduced by 50%. Storage size manageable. FAIL: No performance gain. | 40 | Backend Engineer: Database access
11 | Build monitoring and alerting for PMR-DB. Track calibration drift, query latency, error rates. | Prometheus metrics endpoint | Grafana dashboard showing PMR-DB health metrics, alert rules | N/A | PASS: Dashboard shows real-time metrics. Alerts trigger on calibration drift > 0.1. FAIL: Missing metrics or alerts. | 40 | Backend Engineer: Prometheus/Grafana setup
12 | Final end-to-end testing with complete Matrix22 system. Validate probabilistic reasoning across all modules. | Complete Matrix22 system with real market data | End-to-end test report covering 20+ scenarios | N/A | PASS: All scenarios execute correctly. Outputs match expected behavior. FAIL: Any scenario fails. | 40 | All team members: Complete system integration
12 | Documentation finalization and code cleanup. Prepare for production deployment. Create runbook for operations. | All code and documentation | Production-ready PMR-DB module, operations runbook, deployment guide | N/A | PASS: Documentation complete. Code passes linting. Runbook covers common issues. FAIL: Missing documentation or failing lint checks. | 40 | None

## ML Engineer B - HPVD
Week | Task Description | Input Required | Output Delivered | Synthetic Data Strategy | Pass/Fail Criteria | Est. Hours | Dependencies
1 | Study vector similarity search and embeddings. Read Matrix22 docs (HPVD section, Analog Families). Learn about ANN algorithms (HNSW, IVF), embedding spaces, and similarity metrics. | Matrix22 documentation PDFs (HPVD section, Analog Families, Evolutionary Similarity) | Personal notes covering: (1) Vector similarity concepts, (2) HPVD role in Matrix22, (3) Analog family formation logic | N/A - Learning phase | PASS: Can explain vector similarity search, describe HPVD purpose, and sketch analog family formation process. FAIL: Cannot articulate similarity metrics or analog identification. | 40 | None - independent learning
1 | Set up Python environment with Qdrant, FAISS, PyTorch. Complete vector database tutorial. Implement simple nearest neighbor search on MNIST embeddings. | Python 3.11+, GPU access | Working environment with Qdrant local instance, simple NN search code | Use MNIST dataset for learning | PASS: Qdrant running locally, nearest neighbor search returns correct results on MNIST. FAIL: Installation issues or incorrect neighbors. | 40 | Backend Engineer: GPU instance provisioning
2 | Study time series similarity: Dynamic Time Warping (DTW), Euclidean distance, shape-based similarity. Implement DTW on synthetic trajectories. | Research papers on time series similarity, tslearn library | Time series similarity module (ts_similarity.py) with multiple distance metrics | Generate synthetic trajectories with noise, test DTW vs Euclidean | PASS: DTW correctly aligns shifted series. Multiple metrics implemented. FAIL: DTW gives same results as Euclidean (alignment not working). | 40 | None
2 | Design HPVD module architecture. Define interfaces for Cognitive DNA input, trajectory storage, and analog family output. Write API specifications. | Matrix22 architecture docs, Cognitive DNA format (R16 vector), Trajectory format (60×45 matrix) | HPVD architecture document (hpvd_architecture.md) with data flow diagrams and API specs | N/A | PASS: Architecture clearly separates query formation, similarity search, and family formation. API specs are complete. FAIL: Unclear data flow or missing interfaces. | 40 | ML Engineer C: Cognitive DNA and Trajectory format specifications
3 | Build Cognitive DNA similarity module. Implement cosine similarity, Euclidean distance, and phase proximity scoring. | Synthetic Cognitive DNA vectors (R16) | DNA similarity module (dna_similarity.py) computing phase proximity | Generate 1000 synthetic DNA vectors with known phase clusters | PASS: Similar phases cluster together (silhouette score > 0.6). Different phases separate. FAIL: Random clustering or all equal distances. | 40 | None - uses synthetic data
3 | Implement trajectory-level similarity using shape-based metrics. Combine local and global shape features. | Synthetic trajectories (60×45 matrices) | Trajectory similarity module (traj_similarity.py) combining multiple shape metrics | Generate 500 synthetic trajectories with controlled shape variations | PASS: Similar trajectories score high (>0.8), dissimilar score low (<0.3). FAIL: Uniform scores or inversely correlated with ground truth. | 40 | None - uses synthetic data
4 | Build multi-channel similarity fusion. Combine Cognitive DNA, trajectory, and geometry compatibility into unified similarity score. | DNA similarity scores, trajectory similarity scores, geometry descriptors | Fusion module (similarity_fusion.py) producing unified analog confidence | Mock similarity channels with varying reliability | PASS: Fusion weights reliable channels more. Output is valid probability (0-1). FAIL: Equal weighting ignoring channel quality. | 40 | None - uses synthetic similarity scores
4 | Implement analog neighborhood formation. Use probabilistic soft clustering to group compatible analogs. | Similarity matrix (N×N) for candidate analogs | Neighborhood module (neighborhood.py) forming soft-clustered analog families | Generate similarity matrix with ground truth clusters | PASS: Recovered clusters match ground truth (ARI > 0.7). Soft membership allows overlap. FAIL: Hard clusters or poor cluster quality. | 40 | None - uses synthetic similarity data
5 | Set up Qdrant vector database on local server. Design collection schema for Cognitive DNA and trajectories. | Qdrant documentation, server access | Qdrant instance running, collection schema defined, test data indexed | Index 10,000 synthetic DNA vectors | PASS: Qdrant accepts vectors, nearest neighbor queries return results in <100ms. FAIL: Indexing errors or slow queries. | 40 | Backend Engineer: Qdrant server provisioning
5 | Implement HPVD query formation. Combine current Cognitive DNA and trajectory into query representation for Qdrant. | Current Cognitive DNA (R16) and Trajectory (60×45) | Query module (query.py) formatting input for vector search | Use synthetic current state | PASS: Query format compatible with Qdrant. Embedding dimension matches indexed data. FAIL: Format errors or dimension mismatch. | 40 | None - uses synthetic data
6 | Build analog retrieval pipeline. Query Qdrant for top-K candidates, apply multi-channel similarity scoring, filter by threshold. | Query vector, Qdrant collection | Retrieval module (retrieval.py) returning ranked analog candidates with confidence | Query against synthetic indexed data | PASS: Returns top-K results sorted by confidence. Retrieval time < 500ms for K=100. FAIL: Wrong ordering or timeout. | 40 | None - uses synthetic Qdrant data
6 | Implement analog family formation. Group retrieved candidates into coherent families based on mutual compatibility. | Retrieved analog candidates with similarity scores | Family formation module (family.py) producing final analog families | Retrieved candidates from previous module | PASS: Families contain mutually similar analogs. Intra-family similarity > 0.7. FAIL: Random groupings or single-member families. | 40 | None - uses retrieved candidate data
7 | Integrate HPVD with ML Engineer C geometry module. Test with synthetic trajectories and Cognitive DNA. | ML Engineer C: Synthetic trajectories and Cognitive DNA outputs | Integration test showing HPVD correctly processes geometry module outputs | ML Engineer C provides 50 synthetic trajectory + DNA pairs | PASS: HPVD processes all inputs without errors. Analog families formed correctly. FAIL: Format errors or empty families. | 40 | ML Engineer C: Trajectory and Cognitive DNA modules
7 | Optimize analog retrieval performance. Implement query batching, caching, and index tuning. | Profiling results from retrieval module | Optimized retrieval with 3x speed improvement, cache implementation | N/A | PASS: Query latency reduced by ≥66%. Cache hit rate > 40%. FAIL: No performance improvement. | 40 | None
8 | Index historical trajectory database. Load 10+ years of market trajectories into Qdrant with metadata. | Backend Engineer: Historical trajectory data from TimescaleDB | Qdrant collection with 100K+ historical trajectories indexed | N/A - using real data | PASS: All trajectories indexed successfully. Metadata preserved. Query latency acceptable. FAIL: Indexing failures or missing data. | 40 | Backend Engineer: Historical trajectory data, ML Engineer C: Real trajectory format
8 | Transition from synthetic to real analog search. Test HPVD on real market trajectories and validate results. | Real Cognitive DNA and trajectories from ML Engineer C | HPVD running on real data, validation report showing reasonable analog families | N/A - using real data | PASS: Analog families look structurally similar (visual inspection). Confidence scores distributed reasonably. FAIL: Degenerate families or uniform confidence. | 40 | ML Engineer C: Real Cognitive DNA and trajectories, Backend: Real market data
9 | Full integration with PMR-DB. Provide analog families to ML Engineer A and validate probabilistic reasoning. | Real analog families from HPVD | Integration test showing PMR-DB correctly consumes analog families | N/A | PASS: PMR-DB processes families without errors. Probability distributions look reasonable. FAIL: Format mismatches or PMR-DB errors. | 40 | ML Engineer A: PMR-DB module ready
9 | Backend API integration. Expose HPVD analog search via REST endpoints. | Backend Engineer: API endpoint definitions | HPVD callable via API, test suite passing | N/A | PASS: API returns analog families in JSON. Latency < 1 second. FAIL: API errors or timeouts. | 40 | Backend Engineer: FastAPI infrastructure
10 | Implement advanced similarity metrics: structural topology (persistent homology), regime phase alignment. | Gudhi library, advanced geometry features from ML Engineer C | Advanced similarity module with topological features | Test on synthetic trajectories with known topological structure | PASS: Topological features improve analog selection (precision +10%). FAIL: No improvement or performance degradation. | 40 | ML Engineer C: Topological feature extraction
10 | Load testing HPVD. Test with 1000 concurrent queries. Identify and fix bottlenecks. | 1000 concurrent query requests | Load test report, performance tuning | Generate realistic query load | PASS: System handles load without crashes. P95 latency < 2 seconds. FAIL: Crashes or memory issues. | 40 | Backend Engineer: Load testing infrastructure
11 | Implement incremental trajectory indexing. Add new trajectories to Qdrant without full reindex. | New trajectory stream from market data | Incremental indexing pipeline, update schedule | Simulate daily trajectory updates | PASS: New trajectories indexed within 5 minutes. Search includes new data immediately. FAIL: Indexing lag or stale results. | 40 | Backend Engineer: Real-time data pipeline
11 | Build monitoring and alerting for HPVD. Track analog family quality, query latency, index health. | Prometheus metrics endpoint | Grafana dashboard for HPVD health, alert rules | N/A | PASS: Dashboard shows real-time metrics. Alerts trigger on empty families or high latency. FAIL: Missing metrics or alerts. | 40 | Backend Engineer: Prometheus/Grafana setup
12 | Final end-to-end testing with complete Matrix22 system. Validate analog search across all scenarios. | Complete Matrix22 system with real market data | End-to-end test report covering 20+ market scenarios | N/A | PASS: All scenarios produce reasonable analog families. No crashes or errors. FAIL: Any scenario fails or degenerates. | 40 | All team members: Complete system integration
12 | Documentation finalization and code cleanup. Create operations runbook for HPVD maintenance and monitoring. | All code and documentation | Production-ready HPVD module, operations runbook, deployment guide | N/A | PASS: Documentation complete. Runbook covers index maintenance and troubleshooting. FAIL: Missing operational procedures. | 40 | None

## ML Engineer C - Geometry
Week | Task Description | Input Required | Output Delivered | Synthetic Data Strategy | Pass/Fail Criteria | Est. Hours | Dependencies
1 | Study manifold learning: Riemannian geometry, tangent spaces, geodesics, curvature. Read Matrix22 docs (Structural Geometry, State Vector). Learn dimensionality reduction: PCA, UMAP, autoencoders. | Matrix22 documentation PDFs (Structural Geometry, State Vector, Trajectory, Cognitive DNA) | Personal notes covering: (1) Manifold concepts, (2) LTV/LVC/K definitions, (3) State Vector → Cognitive DNA pipeline | N/A - Learning phase | PASS: Can explain manifold geometry, describe LTV/LVC/K metrics, and sketch State Vector construction. FAIL: Cannot articulate geometric concepts. | 40 | None - independent learning
1 | Set up Python environment with NumPy, Scikit-learn, PyTorch, Geomstats, UMAP. Complete manifold learning tutorials. Implement PCA and UMAP on toy datasets. | Python 3.11+, GPU access | Working environment, PCA and UMAP examples on Swiss Roll dataset | Use Swiss Roll and S-curve datasets for learning | PASS: Environment runs all libraries. PCA and UMAP produce correct low-dimensional embeddings. FAIL: Import errors or incorrect embeddings. | 40 | Backend Engineer: GPU instance provisioning
2 | Design State Vector (R45) construction pipeline. Map 45 KPIs to dimensions. Define normalization schemes (z-score, min-max, regime-aware). | KPI priority table from documentation, sample raw market data | State Vector specification document (state_vector_spec.md) with dimension mapping and normalization formulas | N/A | PASS: All 45 dimensions clearly defined with data sources. Normalization appropriate for each KPI type. FAIL: Ambiguous definitions or missing normalization. | 40 | Backend Engineer: Data schema for raw market data
2 | Implement KPI computation module. Calculate volatility metrics (RV, BV, jump ratio), distribution stats (skew, kurtosis), correlation metrics. | Synthetic OHLCV data | KPI module (kpi_compute.py) computing 45 metrics from raw data | Generate synthetic price series with controlled volatility | PASS: KPI values match manual calculations. All 45 metrics computed. FAIL: Numerical errors or missing metrics. | 40 | None - uses synthetic price data
3 | Build State Vector construction module. Apply normalization, assemble 45-dimensional vector, ensure deterministic output. | Computed KPIs from previous module | State Vector module (state_vector.py) producing R45 vectors with deterministic replay | Use synthetic KPI data | PASS: Output is 45-dimensional. Values normalized to reasonable ranges. Deterministic (same input → same output). FAIL: Dimension errors or non-determinism. | 40 | None - uses synthetic KPI data
3 | Implement trajectory formation. Create rolling 60-timestep windows of State Vectors, forming 60×45 matrices. | Time series of State Vectors (R45) | Trajectory module (trajectory.py) producing 60×45 matrices | Generate 500-timestep State Vector series | PASS: Trajectories correctly windowed. Shape is exactly 60×45. No data leakage. FAIL: Wrong shape or future data included. | 40 | None - uses synthetic State Vector series
4 | Implement Local Total Volume (LTV) computation. Estimate covariance over trajectory, compute determinant/volume. | Trajectory (60×45 matrix) | LTV module (ltv.py) computing volume metric | Synthetic trajectories with controlled dimensionality | PASS: High-dimensional motion → high LTV. Constrained motion → low LTV. FAIL: LTV uncorrelated with dimensionality. | 40 | None - uses synthetic trajectories
4 | Implement Local Volume Collapse (LVC) detection. Track LTV changes relative to baseline, detect sharp contractions. | Time series of LTV values | LVC module (lvc.py) detecting volume collapse events | Generate LTV series with artificial collapse events | PASS: Correctly identifies synthetic collapse events (sensitivity > 0.9). False positive rate < 0.1. FAIL: Misses collapses or high false positives. | 40 | None - uses synthetic LTV series
5 | Implement Intrinsic Dimensionality (K) estimation using PCA or local PCA. Estimate active degrees of freedom. | Trajectory (60×45 matrix) | K estimation module (intrinsic_dim.py) computing effective dimensionality | Synthetic trajectories with known intrinsic dimensionality | PASS: Estimated K matches ground truth ±2 dimensions. FAIL: Large errors (>5 dimensions) or constant K. | 40 | None - uses synthetic trajectories
5 | Build Cognitive DNA compression pipeline. Reduce trajectory from 60×45 → R16 using PCA or autoencoder. Preserve evolutionary phase. | Trajectory (60×45 matrix) | Cognitive DNA module (cognitive_dna.py) producing R16 vectors | Synthetic trajectories with known phase labels | PASS: Similar phases have similar DNA (cosine similarity > 0.8). Different phases separate (cosine < 0.3). FAIL: Random or uninformative DNA. | 40 | None - uses synthetic trajectories
6 | Integrate geometry modules into unified pipeline. Test State Vector → Trajectory → LTV/LVC/K → Cognitive DNA flow. | Synthetic raw market data | Unified geometry pipeline producing all outputs from raw data | End-to-end synthetic data pipeline | PASS: Pipeline runs without errors. All outputs validated. FAIL: Pipeline breaks or incorrect outputs. | 40 | None - uses synthetic data
6 | Implement deterministic replay for entire pipeline. Ensure identical inputs produce identical outputs (random seed control, no non-determinism). | Test dataset with fixed random seed | Replay validation report showing identical outputs across 10 runs | N/A - uses existing test data | PASS: Hash of all outputs identical across runs. FAIL: Any variation detected. | 40 | None
7 | Transition from synthetic to real market data. Integrate with backend data pipeline. Process historical data. | Backend Engineer: Real market data from TimescaleDB | Geometry pipeline running on real data, validation report | N/A - using real data | PASS: Pipeline processes real data without errors. Metrics look reasonable (no NaNs, inf, or degenerate values). FAIL: Crashes or invalid outputs. | 40 | Backend Engineer: Real market data access, data normalization pipeline
7 | Validate LTV/LVC/K metrics on historical market crises (2008 crash, COVID crash, etc.). Verify metrics spike during stress. | Historical crisis period data | Crisis validation report showing LVC spikes and K drops during known stress events | N/A - using historical crisis data | PASS: LVC spikes >3 sigma during 2008/2020 crashes. K drops <10 during crises. FAIL: Metrics uncorrelated with known stress. | 40 | Backend Engineer: Historical crisis data
8 | Optimize geometry pipeline performance. Profile code, vectorize operations, use GPU acceleration where applicable. | Profiling results | Optimized pipeline with 3x speed improvement | N/A | PASS: Processing time reduced by ≥66%. State Vector construction < 10ms per timestep. FAIL: No significant performance gain. | 40 | None
8 | Build historical trajectory database. Process 10+ years of data, store trajectories with metadata (timestamps, world state, geometry metrics). | Backend Engineer: Historical market data (10+ years) | TimescaleDB table with 100K+ trajectories indexed and queryable | N/A - using real historical data | PASS: All trajectories stored with correct metadata. Query latency < 100ms for timestamp-based retrieval. FAIL: Data loss or slow queries. | 40 | Backend Engineer: TimescaleDB setup and historical data
9 | Full integration with HPVD module. Provide Cognitive DNA and trajectories to ML Engineer B, validate analog search. | Real trajectories and Cognitive DNA from pipeline | Integration test showing HPVD correctly consumes geometry outputs | N/A | PASS: HPVD processes outputs without format errors. Analog families formed correctly. FAIL: Format mismatches or HPVD errors. | 40 | ML Engineer B: HPVD module ready
9 | Integration with Manager authorization module. Provide LTV/LVC/K metrics for world state classification. | Real-time geometry metrics | Integration test showing authorization gate correctly reads geometry metrics | N/A | PASS: Authorization gate receives metrics without errors. World state transitions observed. FAIL: Data format issues or missing metrics. | 40 | Manager: Authorization gate module ready
10 | Implement advanced geometry features: curvature estimation, geodesic distances, tangent space stability. | Geomstats library, trajectory data | Advanced geometry module with curvature and geodesic metrics | Test on synthetic manifolds with known curvature | PASS: Curvature estimates match ground truth for synthetic data. FAIL: Large errors or numerical instability. | 40 | None - uses synthetic validation data
10 | Build real-time State Vector streaming pipeline. Process incoming market data with <1 second latency. | Backend Engineer: Real-time market data stream | Streaming pipeline producing State Vectors in real-time | Simulate real-time data feed | PASS: End-to-end latency < 1 second. No data loss. FAIL: Latency >2 seconds or dropped updates. | 40 | Backend Engineer: Real-time data streaming infrastructure
11 | Implement adaptive normalization for State Vector. Handle regime changes and non-stationarity in market data. | Historical regime transition data | Adaptive normalization module handling regime shifts | N/A - uses real regime transition periods | PASS: State Vectors remain stable across regime changes. No outliers during transitions. FAIL: Metrics explode or collapse during shifts. | 40 | Backend Engineer: Regime transition data
11 | Build monitoring and alerting for geometry pipeline. Track State Vector health, geometry metric ranges, pipeline latency. | Prometheus metrics endpoint | Grafana dashboard for geometry health, alert rules | N/A | PASS: Dashboard shows real-time metrics. Alerts trigger on invalid State Vectors or high latency. FAIL: Missing metrics or alerts. | 40 | Backend Engineer: Prometheus/Grafana setup
12 | Final end-to-end testing with complete Matrix22 system. Validate geometry pipeline across all market conditions. | Complete Matrix22 system with real market data | End-to-end test report covering 20+ scenarios | N/A | PASS: All scenarios execute correctly. Geometry metrics stable and meaningful. FAIL: Any scenario produces invalid outputs. | 40 | All team members: Complete system integration
12 | Documentation finalization and code cleanup. Create operations runbook for geometry pipeline monitoring and maintenance. | All code and documentation | Production-ready geometry modules, operations runbook, deployment guide | N/A | PASS: Documentation complete. Runbook covers common issues and troubleshooting. FAIL: Missing operational procedures. | 40 | None

## Manager - Authorization
Week | Task Description | Input Required | Output Delivered | Synthetic Data Strategy | Pass/Fail Criteria | Est. Hours | Dependencies
1 | Study decision theory, state machines, and rule-based systems. Read Matrix22 docs (Authorization Gate, World State, Market Regime). Understand GREEN/YELLOW/RED classification logic. | Matrix22 documentation PDFs (Authorization Gate, World State, Market Regime Kill-Switch) | Personal notes covering: (1) Authorization principles, (2) World state semantics, (3) Threshold policy design | N/A - Learning phase | PASS: Can explain authorization gate purpose, describe world state transitions, and sketch threshold policy. FAIL: Cannot articulate authorization logic. | 20 | None - independent learning
1 | Project kickoff and team coordination. Set up communication channels (Slack, GitHub), schedule weekly check-ins, establish coding standards and Git workflow. | None | Project charter, communication channels, Git repository structure, coding standards document | N/A | PASS: All team members have access to repos and communication channels. Standards documented. FAIL: Missing access or unclear standards. | 20 | Backend Engineer: GitHub repo setup
2 | Design world state classification logic. Define threshold policies for LTV, LVC, K that map to GREEN/YELLOW/RED. | Statistical analysis of historical LTV/LVC/K distributions (from ML Engineer C) | World state policy document (world_state_policy.md) with threshold tables and decision trees | Use synthetic LTV/LVC/K distributions to set initial thresholds | PASS: Thresholds clearly defined with rationale. Decision tree is complete and unambiguous. FAIL: Missing thresholds or contradictory rules. | 30 | ML Engineer C: LTV/LVC/K metric definitions and synthetic data
2 | Design persistence and hysteresis rules. Prevent rapid state oscillations by requiring sustained conditions for transitions. | World state policy document | Hysteresis specification (hysteresis_spec.md) with dwell time requirements and transition rules | N/A | PASS: Hysteresis prevents rapid GREEN↔YELLOW oscillations. Transition requirements clearly stated. FAIL: Allows rapid oscillations or unclear transition rules. | 10 | None
3 | Implement world state classifier. Build rule engine that ingests LTV/LVC/K and outputs GREEN/YELLOW/RED. | Synthetic LTV/LVC/K time series | World state module (world_state.py) classifying market regime | Generate synthetic geometry metrics with known stress events | PASS: Correctly identifies synthetic stress events as YELLOW/RED. Normal periods as GREEN. FAIL: Misclassifications or uniform states. | 30 | ML Engineer C: Synthetic LTV/LVC/K data
3 | Implement state transition logic with hysteresis. Add dwell time counters and transition guards. | World state classifier outputs | State machine module (state_machine.py) with hysteresis logic | Test with oscillating synthetic metrics | PASS: State changes only after dwell time met. No rapid oscillations. FAIL: Immediate transitions without hysteresis. | 10 | None - uses previous module outputs
4 | Build authorization gate logic. Implement rules that block/constrain intelligence based on world state. | World state (GREEN/YELLOW/RED) | Authorization module (authorization.py) returning AUTHORIZED/CONSTRAINED/BLOCKED | Test with synthetic world state sequences | PASS: RED always blocks. YELLOW constrains. GREEN authorizes. FAIL: Wrong authorization for any state. | 30 | None - uses synthetic world state
4 | Implement TTL (time-to-live) for authorization decisions. Decisions expire after specified duration, requiring re-evaluation. | Authorization decision | TTL module (ttl.py) managing authorization expiration | Test with time-advancing simulation | PASS: Authorizations expire correctly. Re-evaluation triggered. FAIL: Stale authorizations or no expiration. | 10 | None
5 | Build reason code generation. Provide human-readable explanations for authorization decisions citing specific thresholds breached. | World state classification details (which metrics triggered state) | Reason code module (reason_codes.py) generating explanations | Test with various world state scenarios | PASS: Reason codes correctly cite breached thresholds. Explanations are clear and grammatically correct. FAIL: Incorrect or unclear reasons. | 30 | None
5 | Coordinate integration planning. Define interfaces between all modules. Create integration test plan. | All team members: Module interface specifications | Integration plan document with module dependencies and test scenarios | N/A | PASS: All interfaces clearly defined. Test plan covers critical paths. FAIL: Ambiguous interfaces or missing test cases. | 10 | All ML Engineers: Module interface specs
6 | Team check-in and dependency resolution. Address any blockers in ML engineer work. Facilitate cross-team collaboration. | Team status reports | Meeting notes, blocker resolution plan | N/A | PASS: All blockers identified and plans made. Team aligned. FAIL: Unresolved blockers or team confusion. | 10 | All team members
6 | Implement deterministic replay for authorization module. Ensure identical geometry inputs produce identical authorization decisions. | Test geometry data with fixed seed | Replay validation report showing deterministic behavior | N/A - uses existing test data | PASS: Authorization decisions identical across 10 runs. FAIL: Any variation detected. | 30 | None
7 | Transition from synthetic to real geometry data. Integrate with ML Engineer C pipeline, test authorization on historical market data. | ML Engineer C: Real LTV/LVC/K metrics from historical data | Authorization module running on real data, validation report | N/A - using real data | PASS: Authorization module processes real data without errors. World state transitions look reasonable for historical crises. FAIL: Crashes or nonsensical state classifications. | 30 | ML Engineer C: Real geometry metrics
7 | Validate authorization logic on historical market crises. Verify that 2008/2020 crashes trigger RED states. | Historical crisis period geometry data | Crisis validation report showing RED states during known stress events | N/A - using historical crisis data | PASS: 2008 and 2020 crashes trigger RED. Calm periods show GREEN. FAIL: Wrong states during known crises. | 10 | ML Engineer C: Historical crisis geometry metrics
8 | Full integration with PMR-DB. Provide world state constraints to ML Engineer A, validate that reasoning respects authorization. | World state outputs, PMR-DB reasoning results | Integration test showing PMR-DB respects authorization constraints | N/A | PASS: PMR-DB blocks reasoning in RED, constrains in YELLOW, operates fully in GREEN. FAIL: PMR-DB ignores world state. | 30 | ML Engineer A: PMR-DB module ready
8 | Backend API integration. Expose authorization gate via REST endpoints. | Backend Engineer: API endpoint definitions | Authorization callable via API, test suite passing | N/A | PASS: API returns authorization decisions with reason codes. Latency < 100ms. FAIL: API errors or timeouts. | 10 | Backend Engineer: FastAPI infrastructure
9 | Coordinate full system integration testing. Define end-to-end test scenarios covering all world states and module interactions. | All team members: Module integration status | System integration test plan with 20+ scenarios | N/A | PASS: Test plan covers all critical paths and edge cases. FAIL: Missing scenarios or incomplete coverage. | 20 | All team members: Modules integrated with backend
9 | Execute integration testing. Run all test scenarios, document failures, coordinate fixes. | Integration test plan | Integration test report with pass/fail status for each scenario | N/A | PASS: >90% scenarios pass. Critical failures identified and triaged. FAIL: <80% pass rate or critical unidentified failures. | 20 | All team members: Complete module integration
10 | Build comprehensive monitoring dashboard. Track world state distribution, authorization decision rates, reason code frequency. | Prometheus metrics from authorization module | Grafana dashboard for authorization system health | N/A | PASS: Dashboard shows real-time world state, authorization rates, and reason codes. FAIL: Missing key metrics. | 20 | Backend Engineer: Prometheus/Grafana setup
10 | Implement alerting for critical authorization events. Alert on sustained RED states, authorization failures, threshold breaches. | Grafana alert configuration | Alert rules for critical authorization events | N/A | PASS: Alerts trigger correctly on test scenarios (e.g., simulated RED state). FAIL: Alerts don't fire or false positives. | 20 | Backend Engineer: Alerting infrastructure
11 | Develop operations runbook for authorization system. Document common failure modes, troubleshooting procedures, threshold tuning guidelines. | All code and test results | Authorization operations runbook | N/A | PASS: Runbook covers common issues with clear procedures. Threshold tuning guidelines included. FAIL: Missing critical procedures or unclear instructions. | 20 | None
11 | Coordinate pre-production readiness review. Ensure all modules meet production standards (documentation, tests, monitoring). | All team members: Module completion status | Production readiness report with go/no-go decision | N/A | PASS: All modules meet criteria. Clear path to production. FAIL: Critical gaps identified. | 20 | All team members: Module completion
12 | Final end-to-end testing with complete Matrix22 system. Execute production readiness tests. | Complete Matrix22 system | Production readiness test report | N/A | PASS: All production scenarios pass. System stable under load. FAIL: Any critical failure. | 20 | All team members: Complete system integration
12 | Project wrap-up and handoff. Finalize documentation, conduct knowledge transfer, plan post-launch support. | All documentation and code | Project completion report, handoff documentation, support plan | N/A | PASS: Complete documentation delivered. Support plan in place. FAIL: Missing documentation or unclear support process. | 20 | All team members

## Backend Engineer
Week | Task Description | Input Required | Output Delivered | Synthetic Data Strategy | Pass/Fail Criteria | Est. Hours | Dependencies
1 | Study Matrix22 architecture and data flow. Read all documentation to understand end-to-end pipeline. Learn about FastAPI, TimescaleDB, Qdrant, and system integration patterns. | Matrix22 documentation PDFs (all sections) | Personal notes covering: (1) Data pipeline architecture, (2) Database requirements, (3) API endpoints needed | N/A - Learning phase | PASS: Can describe end-to-end data flow and identify critical integration points. FAIL: Unclear on system architecture. | 40 | None - independent learning
2 | Set up AWS infrastructure. Provision EC2 instances (GPU, CPU, backend), configure VPC, security groups, and IAM roles. | AWS account, infrastructure requirements from Master Guide | Running AWS infrastructure, network configuration documented | N/A | PASS: All instances running, network configured, team has access. FAIL: Instance errors or network issues. | 40 | None - has AWS credentials
3 | Set up databases. Deploy PostgreSQL, TimescaleDB extension, Qdrant vector database, and Redis cache. Configure backups. | Database requirements, server access | All databases running with backups configured, connection strings documented | N/A | PASS: All databases accessible, backup jobs scheduled. FAIL: Database connection issues or no backups. | 40 | None - has server access
4 | Design database schemas for State Vectors, trajectories, authorization logs, and evidence graphs. Implement in PostgreSQL/TimescaleDB. | Data format specifications from ML Engineers | Database schema scripts (SQL), migration system set up | N/A | PASS: Schemas support all required data types. Indexes defined for common queries. FAIL: Missing tables or no indexing strategy. | 40 | ML Engineers: Data format specifications
5 | Build data ingestion pipeline. Connect to market data APIs (Polygon.io, Yahoo Finance), implement data validation and normalization. | Data vendor API keys, normalization requirements | Data ingestion service pulling real-time and historical market data | Start with Yahoo Finance (free), then add Polygon | PASS: Data flows into database without errors. Normalization applied correctly. FAIL: Missing data or validation failures. | 40 | None - API keys provided
6 | Implement FastAPI backend structure. Set up project layout, routing, dependency injection, configuration management. | API endpoint specifications | FastAPI application skeleton with basic health check endpoint | N/A | PASS: API starts successfully, health check returns 200. FAIL: Startup errors. | 40 | None
7 | Build API endpoints for geometry module. Expose State Vector, trajectory, and LTV/LVC/K data. | ML Engineer C: Geometry module integration | API endpoints: GET /state-vectors, GET /trajectories, GET /geometry-metrics | N/A | PASS: Endpoints return valid JSON data from ML Engineer C module. FAIL: API errors or data format issues. | 40 | ML Engineer C: Geometry module ready for integration
8 | Build API endpoints for HPVD. Expose analog search functionality. | ML Engineer B: HPVD module integration | API endpoints: POST /analog-search (accepts trajectory, returns families) | N/A | PASS: Endpoint accepts trajectory input and returns analog families. FAIL: Integration errors. | 40 | ML Engineer B: HPVD module ready
9 | Build API endpoints for PMR-DB and authorization. Expose probabilistic reasoning and authorization decisions. | ML Engineer A: PMR-DB module, Manager: Authorization module | API endpoints: POST /reasoning (accepts analogs, returns probabilities), GET /authorization (returns current world state and decision) | N/A | PASS: Endpoints integrate with ML modules correctly. FAIL: Integration errors. | 40 | ML Engineer A: PMR-DB ready, Manager: Authorization ready
10 | Implement authorization log persistence. Store all authorization decisions with timestamps, world state, and reason codes. | Authorization decisions from Manager module | PostgreSQL table with authorization logs, API endpoint GET /authorization-logs | N/A | PASS: Logs persisted correctly with all metadata. API retrieves logs efficiently. FAIL: Data loss or slow queries. | 40 | Manager: Authorization module
11 | Implement evidence graph storage. Store graph structure in PostgreSQL, enable traceability queries. | ML Engineer A: Evidence graph data | PostgreSQL tables for graph nodes/edges, API endpoint GET /evidence-graph/{decision_id} | N/A | PASS: Graph stored correctly. Traceability queries return full reasoning path in <1 second. FAIL: Graph storage errors or slow retrieval. | 40 | ML Engineer A: Evidence graph module
12 | Implement WebSocket support for real-time updates. Push world state changes and authorization decisions to frontend. | Frontend Engineer: WebSocket requirements | WebSocket endpoint wss://api/ws streaming real-time updates | N/A | PASS: Frontend receives real-time updates without polling. FAIL: WebSocket connection issues. | 20 | Frontend Engineer: WebSocket client ready
12 | Set up monitoring (Prometheus + Grafana) and logging (ELK stack). Instrument API with metrics. | None | Prometheus scraping metrics, Grafana dashboard for API health, ELK collecting logs | N/A | PASS: Metrics visible in Grafana. Logs queryable in Kibana. FAIL: Missing metrics or logs. | 20 | None

## Frontend Engineer
Week | Task Description | Input Required | Output Delivered | Synthetic Data Strategy | Pass/Fail Criteria | Est. Hours | Dependencies
1 | Study Matrix22 UI/UX requirements. Read documentation on world state visualization, evidence graphs, and authorization decisions. Design initial wireframes. | Matrix22 documentation PDFs (Output Layer, Market Regime UI) | UI wireframes for 5 main screens: Dashboard, World State, Geometry Metrics, Evidence Graph, Authorization Logs | N/A - Design phase | PASS: Wireframes cover all required screens with clear information hierarchy. FAIL: Missing screens or unclear layouts. | 40 | None - independent design
2 | Set up React development environment. Initialize Vite project with TypeScript, install dependencies (React Query, Zustand, Recharts, D3, shadcn/ui, Tailwind). | None | Running React dev environment, component library installed | N/A | PASS: Dev server runs, all libraries imported successfully. FAIL: Build errors or missing dependencies. | 40 | None
3 | Build component architecture and design system. Create reusable components: Card, Button, Badge (GREEN/YELLOW/RED), Chart wrapper, etc. | Design system specifications | Component library in /components folder, Storybook setup (optional) | N/A | PASS: All base components built and styled consistently. FAIL: Inconsistent styling or missing components. | 40 | None
4 | Build World State dashboard. Display current state (GREEN/YELLOW/RED) with visual indicators, show reason codes, display TTL countdown. | Mock world state API responses | World State screen rendering mock data, updates when data changes | Mock API returning random world states | PASS: World state displayed prominently. Color coding correct. Reason codes shown. FAIL: Display errors or missing information. | 40 | None - uses mock data
5 | Build Geometry Metrics dashboard. Chart LTV, LVC, K over time using Recharts. Show historical trends and current values. | Mock geometry metrics time series | Geometry Metrics screen with 3 time series charts | Mock API returning synthetic LTV/LVC/K data | PASS: Charts render correctly. Time axis labeled properly. Current values highlighted. FAIL: Chart errors or unclear presentation. | 40 | None - uses mock data
6 | Build Evidence Graph visualization using D3.js. Display directed graph showing analog → trajectory → outcome links. | Mock evidence graph data (JSON with nodes and edges) | Evidence Graph screen rendering interactive graph | Mock API returning synthetic graph with 50 nodes | PASS: Graph renders without errors. Nodes clickable for details. Layout readable. FAIL: Graph rendering errors or unreadable layout. | 40 | None - uses mock graph data
7 | Build Authorization Log viewer. Display table of past authorization decisions with timestamps, world state, and reason codes. Add filtering and search. | Mock authorization log data | Authorization Log screen with sortable/filterable table | Mock API returning 100 log entries | PASS: Table renders all data. Sorting/filtering works. FAIL: Missing data or broken filters. | 40 | None - uses mock data
8 | Integrate with real backend API. Replace mock data with React Query hooks calling FastAPI endpoints. | Backend Engineer: API documentation and endpoint URLs | All screens fetching real data from API | N/A - using real API | PASS: All screens load real data without errors. Loading states shown. FAIL: API errors or missing data. | 40 | Backend Engineer: API endpoints deployed
9 | Implement WebSocket integration for real-time updates. Subscribe to world state and geometry metric streams. | Backend Engineer: WebSocket endpoint | Real-time UI updates without polling | N/A | PASS: UI updates immediately when world state changes. No polling. FAIL: Stale data or WebSocket errors. | 40 | Backend Engineer: WebSocket endpoint
10 | Implement responsive design and mobile support. Ensure dashboard works on tablets and phones. | None | Responsive layouts for all screens, tested on multiple screen sizes | N/A | PASS: All screens usable on mobile (iPhone/Android). Charts scale correctly. FAIL: Broken layouts on mobile. | 40 | None
11 | Accessibility improvements. Ensure WCAG 2.1 AA compliance. Add keyboard navigation, screen reader support, color contrast. | Accessibility testing tools (axe, Lighthouse) | WCAG 2.1 AA compliant dashboard, accessibility audit report | N/A | PASS: No critical accessibility issues. Keyboard navigation works. FAIL: WCAG violations or unusable with keyboard. | 40 | None
12 | Performance optimization and final polish. Implement code splitting, lazy loading, optimize bundle size. Fix bugs. | Performance profiling results | Optimized production build, <3MB bundle size, Lighthouse score >90 | N/A | PASS: Bundle size reduced. Lighthouse performance score >90. FAIL: Large bundle or poor performance. | 20 | None
12 | Final testing and deployment prep. E2E testing with Playwright/Cypress. Create deployment documentation. | Complete integrated system | E2E test suite passing, deployment guide | N/A | PASS: All E2E tests pass. Deployment documented. FAIL: Test failures or missing deployment docs. | 20 | Backend Engineer: Production API